## Project Stage Mileage Graph (2) (hidden)
Sum of Miles
100%

## Development Stage Definitions
Development stage | Definition
Newly Proposed | Identified in WestTEC study but not included in a utility or developer plan.
Conceptual Planning | Explicitly identified as conceptual or planned beyond the 10-year horizon in utility or developer planning documents.
Advanced Planning | Listed as planned in a utility's 10-year transmission plan or other regulator filings, and/or included in a utility or developer's capital budget.
Permitting | Permitting activities, including ROW applications, CPCNs, CECs, and other state/federal permits, are underway. Some projects are permitted but not under construction.
Under Construction | Physical construction activities have begun.
In Service | Project has entered commercial operation.
Cancelled | Project will not move on.
ROW = Right of Way
CPCN = Certificate of Public Convenience Necessity
CEC = Certificate of Environmental Compatibility

## Development Stage Assignment
WestTEC Project Name (Developer's project name if different) | Project Type | Voltage | Cost ($M) | Miles | Transmission Developer | State | Development Stage | Development Stage Notes | Development Stage Source #1 | Development Stage Source #2
Additional TWE Phase Shifter | New Phase-Shifter |  | 41 | N/A | None Identified | Utah | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Arroyo Phase Shifter #2 | New Phase-Shifter |  | 31 | N/A | None Identified | New Mexico | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Ault-Husky 230kV Line Upgrade | Rebuild | 230 kV | 9 | 5 | Public Service Company of Colorado (Xcel Energy) | Colorado | In Service | No clear record that its in service, but construction is complete | NCAP-Construction-Progress-Update_May-2024
Big Sandy- Burlington 230kV Uprate | Rebuild | 230 kV | 8 | 81 | Tri-State | Colorado | Advanced Planning | No CPCN required for uprate. Expected in-service date is 2028. | TSGT 2025 Annual Progress Report | 2024 Rule 3627 Combined 10-Year Report.pdf
Bolo Tie | New Line | 345 kV | 168 | 35 | Pattern Energy | New Mexico | Permitting | Filed Notice of Right-Of-Way Application with the NMPRC in August 2026. | Bolo Transmission Open Solicitation | ROW Application
Bonanza Substation | Substation |  | 300 | N/A | BPA | Oregon | Advanced Planning | Project will complete scoping in Fall 2026. | EGP-10-Project-Summaries.pdf | August 19 GAT Update Workshop
Bonanza to Lower Columbia 500kV Reinforcement Project- Longhorn to Bonanza Line | New Line | 500 kV | 1300 | 274 | BPA | Oregon | Advanced Planning | Scoping starts in Q3/Q4 2026 and estimated ISD is 2035 | August 19 GAT Update Workshop | GERP-Project-Update.pdf
Bouse Upgrade | New Line | 230 kV | 47 | 20 | WAPA | Arizona, California | Permitting | WAPA released final EA in 2022 and a FONSI in 2023 | Project Link: Bouse Upgrade Project, DOE/EA-2106 – Western Area Power Administration | Bouse_Upgrade_FinalEA_061522.pdf
Colorado's Power Pathway Segment 1 - Fort St. Vrain to Canal Crossing | New Line | 345 kV | 249 | 74 | Public Service Company of Colorado (Xcel Energy) | Colorado | In Service | In service in 2026. | Project Description - Xcel Energy Colorado Power Pathway | Att-T_CostSchedulefromCPCN
Colorado's Power Pathway Segment 2 - Canal Crossing to Goose Creek | New Line | 345 kV | 493 | 145 | Public Service Company of Colorado (Xcel Energy) | Colorado | In Service | In service in spring 2025. | Project Description - Xcel Energy Colorado Power Pathway | Att-T_CostSchedulefromCPCN
Colorado's Power Pathway Segment 3 - Goose Creek to May Valley | New Line | 345 kV | 206 | 57 | Public Service Company of Colorado (Xcel Energy) | Colorado | In Service | In service in spring 2025. | Project Description - Xcel Energy Colorado Power Pathway | Att-T_CostSchedulefromCPCN
Colorado's Power Pathway Segment 4 - May Valley to Sandstone to Tundra | New Line | 345 kV | 380 | 130 | Public Service Company of Colorado (Xcel Energy) | Colorado | Under Construction | Under construction 2025-2027. Expected in-service in 2027. | Project Description - Xcel Energy Colorado Power Pathway | Att-T_CostSchedulefromCPCN
Colorado's Power Pathway Segment 5 - Sandstone to Harvest Mile | New Line | 345 kV | 367 | 124 | Public Service Company of Colorado (Xcel Energy) | Colorado | Under Construction | Under construction 2025-2027. Expected in-service in 2027. | Project Description - Xcel Energy Colorado Power Pathway | Att-T_CostSchedulefromCPCN
Colstrip- Broadview 500kV Series Capacitor Upgrade | Series Capacitor | 500 kV | 67 | N/A | None Identified | Montana | Conceptual Planning | Idenified as newly proposed in WestTEC. First identified in MRDAP, Colstrip Transmission System owners have been pursuing the upgrade via initial conversations. | WestTEC_10-year_Full_Report.pdf | Montana Renewables Development Action Plan.pdf
Cross Cascades North Upgrade TSEP 2022 | Reconductor | 500 kV | 400 | 77 | BPA | Washington | Advanced Planning | All three components of the upgrades are planned to complete scoping in Spring 2026. | August 19 GAT Update Workshop | EGP-20-Public-Workshop-17-Oct-2024.pdf
Cross Cascades Project | New Line | 230 kV | 3700 | 235 | Puget Sound Electric | Washington, Oregon | Advanced Planning | Estimated in-service date is 2033. | PSE_Plan_2023_Final.pdf
Energize the existing Red Butte- St. George Line at 345kV | New Line | 345 kV | 75 | 20 | PacifiCorp | Utah | Advanced Planning | Existing line operating at 138 kV; conversion to 345 kV was approved as a near-term planned project with an October 15, 2026 target in-service date as of December 2022. Full project included upgrades at St. George substation, which is currently in NEPA permitting. Current construction status and whether that schedule remains on track are not publicly confirmed, but it is likely delayed. | Transmission System Plan Draft Report | BLM National NEPA Register ¦ DOI-BLM-UT-C030-2026-0040-CE Project Home
Energy Gateway (Segment A Wallula to McNary) | New Line | 230kV | 106 | 30 | PacifiCorp | Washington, Oregon | In Service | Placed in service January 2019 | West of Hemingway
Energy Gateway (Segment B Honeyville to Populus) | Rebuild | 345 kV, 138 kV | 379 | 107 | PacifiCorp | Utah, Idaho | Permitting | Survey and right-of-way June 2025-March 2028, Permitting Jan 2026-Jan 2028 | Project Website: Segment B Honeyville to Populus and Threemile Knoll
Energy Gateway (Segment B Populus to Terminal) | New Line | 345 kV | 478 | 135 | PacifiCorp | Utah | In Service | In service in November 2010 | Gateway Central
Energy Gateway (Segment C Limber to Terminal) | New Line | 500/345/138 kV | 184 | 52 | PacifiCorp | Utah | Advanced Planning | Design & engineering: Feb 2023-2027; Permitting in Q1 2027 | Project Website Gateway Central
Energy Gateway (Segment C Mona to Oquirrh) | New Line | 500kV | 354 | 100 | PacifiCorp | Utah | In Service | In service in 2013 | Gateway Central
Energy Gateway (Segment D.1 Windstart to Aeolus) | New Line | 230kV | 209 | 59 | PacifiCorp | Wyoming | In Service | In service in November 2024 | Gateway West
Energy Gateway (Segment D.2 Aeolus to Bridger/Anitcline) | New Line | 500kV | 496 | 140 | PacifiCorp | Wyoming | In Service | In service in November 2020 | Gateway West
Energy Gateway (Segment D.3 Bridger/Anticline to Populus) | New Line | 500 kV | 708 | 200 | PacifiCorp | Wyoming, Idaho | Advanced Planning | Line is scheduled in service 2034 at the earliest. | Project Website: Gateway West
Energy Gateway (Segment E Populus to Hemingway) | New Line | 500 kV | 2182 | 616 | PacifiCorp | Idaho | Permitting | Local and state permitting began in January 2025. | Project Website: Gateway West Segment E-8
Energy Gateway (Segment F Aeolus to Mona/Clover) | New Line | 500kV | 1474 | 416 | PacifiCorp | Wyoming, Utah | In Service | In service in November 2024 | Gateway South
Energy Gateway (Segment G Sigurd to Red Butte) | New Line | 345kV | 170 | 602 | PacifiCorp | Utah | In Service | In service in 2015 | Gateway South
Greenlink North | New Line | 525 kV | 1380 | 235 | NV Energy | Nevada | Permitting | Record of decision publication expected in 2026. NEPA status in progress (analysis and document preparation). | Project Website: Nevada ¦ NV Energy | BLM Project Permitting Tracker
Greenlink West | New Line | 525 kV | 2820 | 350 | NV Energy | Nevada | Under Construction | Ground breaking in April 2025. Expected in service by May 2027. | Project Website: Greenlink Nevada ¦ NV Energy
Humboldt to Collinsville 500kV Line | New Line | 500 kV | 2740 | 260 | CAISO - California Grid Holdings LLC (CalGrid) | California | Advanced Planning | In May 2025, CAISO selected California Grid Holdings LLC as the approved project sponsor for the project. | 2023-2024 Transmission Planning Process: Approved Project Sponsor Selection Reports Posted ¦ California ISO | CAISO 2023-2024 Transmission Plan
Humboldt to Fern Road 500kV Line | New Line | 500 kV | 1400 | 140 | CAISO - California Grid Holdings LLC (CalGrid) | California | Advanced Planning | In May 2025, CAISO selected California Grid Holdings LLC as the approved project sponsor for the project. | 2023-2024 Transmission Planning Process: Approved Project Sponsor Selection Reports Posted ¦ California ISO | CAISO 2023-2024 Transmission Plan
Boardman to Hemingway | New Line | 500 kV | 1200 | 290 | Idaho Power | Idaho, Oregon | Under Construction | Construction began in 2025 and is on track for completion in late 2027. | Project Website: Purpose and Need - Idaho Power
Montana to Washington | Uprate | 500 kV | 545 | 90 | BPA | Washington, Montana, Idaho | Permitting | Enviromental Assessment determination (if warranted) expected Winter 2026/27, Final EA (if warranted) expected Fall 2027, expected construction start Summer 2029 | Project Website: Montana-to-Washington Transmission System Upgrade Project (M2W) - Bonneville Power Administration | NEPA Application
New 345/230kV Transformer at Copper Verde | New Transformer | 345/230 kV | 10 | N/A | None Identified | Arizona | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New 345/230kV Transformer at Grand Junction | New Transformer | 345/230 kV | 10 | N/A | None Identified | Colorado | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New 345/230kV Transformers at Bridger and Sigurd | New Transformer | 345/230 kV | 26 | N/A | None Identified | Utah/Wyoming | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New 345/230kV Transformers at Liberty and Peacock | New Transformer | 345/230 kV | 29 | N/A | None Identified | Arizona | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New 500/345kV Transformer at Coronado | New Transformer | 500/345 kV | 20 | N/A | None Identified | Arizona | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New 500/345kV Transformer at Walker River | New Transformer | 500/345 kV | 19 | N/A | None Identified | Nevada | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New Afton North-Airport | New Line | 345 kV | 2 | 12 | El Paso Electric | New Mexico | Permitting | CPCN filed in July 2026 | CPCN NM Docket: #26-0000137 | Notice of NMSLO Public Meeting for Project
New Afton-Afton North | New Line | 345 kV | 2 | 1 | El Paso Electric | New Mexico | Advanced Planning | Mentioned in Bustillos Testimony-- CCN filed for New Afton North- Airport and "EPE plans to file additional CCN applications for other proposed new 345kv lines" which includes Afton-Afton North | EPE 2024 Annual Progress Report | Bustillos Testimony
New Badger Creek- Big Sandy 230kV Line | New Line | 230 kV | 86 | 80 | Tri-State | Colorado | Permitting | CPCN granted. Expected in-service in 2028. Unclear whether construction has begun. | Appendix E - Tri-State Project Sheets.pdf | 2024 Rule 3627 Combined 10-Year Report.pdf
New Bethel- Round Butte 500kV Line | New Line | 500 kV | 857 | 100 | Portland General Electric | Oregon | Permitting | Currently in the permit scoping and application preparation stage. | Project Website
New Bonanza- La Pine 230kV line | New Line | 230 kV | 150 | 53 | BPA | Oregon | Advanced Planning | Project has recently kicked off scoping. Estimated ISD is 2032. | August 19 GAT Update Workshop | GERP-Project-Update.pdf
New Boone-Huckleberry 230kV Line | New Line | 230 kV | 40 | 30 | Tri-State | Colorado | Under Construction | CPCN granted. Expected in-service in 2026. Unclear whether construction has begun, but likely. | Appendix E - Tri-State Project Sheets.pdf | 2024 Rule 3627 Combined 10-Year Report.pdf
New Burlington- Lamar 230kV Line | New Line | 230 kV | 107 | 107 | Tri-State | Colorado | In Service | In service in 2025. | TSGT 2025 Annual Progress Report | Tri-State energizes Burlington-Lamar transmission line ¦ Tri-State Generation and Transmission Association, Inc
New Corral- Grassland Annex 500kV line | New Line | 500 kV | 659 | 159 | PacifiCorp | Oregon | Conceptual Planning | Full Circle–Apex 500 kV, formerly Corral–Grassland Annex: beyond PacifiCorp’s 10-year planning horizon | PacifiCorp 2026 Progress Report
New Corral- Snow Goose 500kV line | New Line | 500 kV | 763 | 161 | PacifiCorp | Oregon | Advanced Planning | Snow Goose–Full Circle 500 kV, formerly Corral–Snow Goose: in routing and pre-permitting development; targeted for service in Q4 2034. | PacifiCorp 2026 Progress Report | NWEC-MT-Regional-Transmission-Connectivity-Study-Report-1.pdf
New Four Corners- Pintado Circuit 2 | New Line | 345 kV | 312 | 81 | PNM | New Mexico | Conceptual Planning | PNM includes Four Corners to Rio Puerco and Ambrosia to West Mesa and Ambrosia to Coronado in their utility report. These projects meet the same Albuquerque to Arizona transmission need that this project meets. | 20-Year Transmission Planning Outlook
New Four Corners- San Juan Circuit 2 | New Line | 345 kV | 49 | 10 | PNM | New Mexico | Conceptual Planning | PNM includes Four Corners to Rio Puerco and Ambrosia to West Mesa and Ambrosia to Coronado in their utility report. These projects meet the same Albuquerque to Arizona transmission need that this project meets. | 20-Year Transmission Planning Outlook
New Golden Valley 230kV Transmission Line Project | New Line | 230 kV | 64 | 17 | UniSource Energy Services | Arizona | Permitting | ACC CEC granted in June 2021. BLM Decision granted in September 2021. Estimated to be in-service in 2030. No construction has begun. | Project Website: Golden Valley 230 kV – UniSource Energy Services
New Grassland Annex- B2H Tap Substation 500kV Line | New Line | 500 kV | 76 | 16 | PacifiCorp | Oregon | Permitting | Apex–Maverick 500 kV, formerly Grassland Annex–B2H Tap: in development and permitting; Apex substation under construction, line construction planned for 2027–2029. | Project Website: https://www.pacificorp.com/transmission/transmission-projects/apex-to-maverick.html
New Harborton- Trojan #3 & #4 230kV Line | new Line | 230 kV | 135 | 33 | Portland General Electric | Oregon | Conceptual Planning | Harborton–Trojan #3 in earliest-stage planning; #3 targeted for April 2035, with no project-specific permitting or construction underway; #4 is not listed in PGE’s current plan and has no confirmed schedule. | Integrated Resource Planning Roundtable Presentation
New Hassayampa Pinal West #2 Line | New Line | 500 kV | 244 | 51 | Salt River Project | Arizona | Permitting | CEC granted. Project is fully permitted but requested an extension. Construction has not started yet. | Project Website: Palo Verde to Pinal West 500 kV transmission project ¦ SRP | Amend CEC to extend time limitation
New Hemingway to Bowmont #2 230kV Line | New Line | 230 kV | 29 | 13 | Idaho Power | Idaho | Advanced Planning | Listed as a project planned for 1 to 5 year horizon in Idaho Power's 2024-2025 local transmission plan. No record that permitting has begun. | IPCO_2025_Final_Local_Transmission_Plan | Microsoft Word - Idaho Power 2026 WECC Annual Supplemental Progress Report.docx
New Hubbard to Bowmont 230kV Line | New Line | 230 kV | 36 | 16 | Idaho Power | Idaho | Under Construction | Permitted in 2022. Phased construction timeline from 2023-2026. | Project Website: Bowmont to Hubbard Transmission Line - Idaho Power | Bowmont_to_Hubbard_Fact_Sheet.pdf
New Jojoba to Rudd 500kV Line | New Line | 500 kV | 146 | 31 | Arizona Public Service | Arizona | Advanced Planning | Right of way and siting workshops in October 2026. Expected in-service in 2031/32. | Project Website: Cotton Transmission Corridor 500kV/230kV ¦ APS | 2023-2032_Ten_Year_Transmission_Plan
New Lantern- Comstock Meadows 345kV Line | New Line | 345 kV | 124 | 33 | NV Energy | Nevada | Advanced Planning | Estimated in service in 2028. There are limited updates on it's development. | NVE 2026 Annual Progress Report
New Manning-Metcalf 500kV Line | New Line | 500 kV | 700 | 100 | CAISO - California Grid Holdings LLC (CalGrid) | California | Advanced Planning | Project included in 2024-25 CAISO plan; project sponsor selected in 2026. Expected in-service in 2034. | 2024-2025 Transmission Planning Process: Approved project sponsor selection report for Manning – Metcalf 500kV Transmission Line Project posted ¦ California ISO
New Mayfield 230kV Substation and Transmission Lines | New Line | 230 kV | 32 | 8 | Idaho Power | Idaho | Permitting | Submitted a CUP in 2025 and listed in IPCO 2025 Local Transmission Plan. Substation construction to begin in fall 2026. | Project Website: Mayfield Substation and Transmission Project - Idaho Power | CUP application
New Mayfield Substation to Boise Bench Substation 230kV Line | New Line | 230 kV | 50 | 20 | Idaho Power | Idaho | Advanced Planning | Listed in IPCO's 2024 Eastern Treasure Valley Electricity Plan | ETVEP Update
New Mayfield Substation to Chip Substation 230kV Line | New Line | 230 kV | 41 | 16 | Idaho Power | Idaho | Advanced Planning | Listed in IPCO's 2024 Eastern Treasure Valley Electricity Plan | ETVEP Update
New Mayfield Substation to South Boise Substation 230kV Line | New Line | 230 kV | 45 | 21 | Idaho Power | Idaho | Advanced Planning | Listed in IPCO's 2024 Eastern Treasure Valley Electricity Plan | ETVEP Update
New Mead- Liberty- West Wing | New Line | 500 kV | 1418 | 273 | None Identified | Arizona | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New Imperial Valley-North of SONGS 500kV Line and Substation (Line = Golden Pacific Powerlink, substation = North of SONGS 500/230kv substation) | New Line | 500 kV | 2280 | 145 | CAISO - San Diego Gas & Electric Company and Horizon West Transmission, LLC | California | Advanced Planning | Project approved in 2022-2023 plan; Line and substation was awarded to Horizon West in 2024; Line portion was transferred to San Diego Gas and Electric in 2025 and renamed Golden Pacific Powerlink; estimated projected in service date 2032 | CAISO / CPUC Transmission Development Forum HWT Project Updates | CAISO 2022-2023 Transmission Plan
New North Gila- Imperial Valley #2 500kV line (Ironwood Transmission) | New Line | 500 kV | 340 | 85 | CAISO - Horizon West Transmission LLC | Arizona/California | Permitting | CPCN and Environmental assessment submitted in September 2025 for California portion. Construction expected to being in 2029; expected in-service in 2030. | Home ¦ Ironwood Transmission Line | CPCN application
New San Jose Area HVDC 230kV Line (Power South Bay Project) | New Line | 230 kV | 726 | 12 | CAISO - LS Power | California | Under Construction | Project included in 2022-23 CIASO plan as HVDC project; Project sponsor selected in 2023; Permitting begun in 2024; CAISO reassesses project and replaces concept with 230kV AC; CPUC reports construction began in March 2026; expected in-service in 2028. | About the Projects – Power The Bay
New North of SONGS-Serrano 500kV Line | New Line | 500 kV | 503 | 31 | CAISO - Lotus Infrastructure Global Operations and Southern Califonia Edison | California | Advanced Planning | Project included in 2022-23 CAISO plan; project sponsor selected in 2024. Expected in-service in 2034 | CAISO 2022-2023 Transmission Plan | 2022-2023 Transmission Planning Process: North of SONGS - Serrano 500kV Line Project Report ¦ California ISO
New Oquirrh-Terminal #3 and #4 Double Circuit Line | New Line | 345 kV | 52 | 14 | PacifiCorp | Utah | In Service | In-service in December 2025. | PacifiCorp 2026 Annual Progress Report
New Pinal Central-ED5 230kV Line | New Line | 230 kV | 44 | 19 | WAPA | Arizona | Under Construction | Expected in-service in Q4 2026. | WAPA 2026 Annual Progress Report
New Rio Puerco- Prosperity (Rio Puerco to Pajarito To Prosperity 345 kV Transmission Project) | New Line | 345 kV | 195 | 36 | PNM | New Mexico | Permitting | Right of way and siting complete. CPCN filed in 2026. Expected in-service in 2029. | CPCN NM Docket: #26-0000041 | pnm.com/pajarito-riopuerco
New Rio Puerco- San Juan Circuit 2 | New Line | 345 kV | 163 | 41 | PNM | New Mexico | Conceptual Planning | PNM includes Four Corners to Rio Puerco and Ambrosia to West Mesa and Ambrosia to Coronado in their utility report. These projects meet the same Albuquerque to Arizona transmission need that this project meets. | 20-Year Transmission Planning Outlook
New Serrano-Del Amo-Mesa 500kV Line | New Line | 500 kV | 1125 | 41 | CAISO | California | Cancelled | CAISO selected project in 2022-23 plan and cancelled project in 2025-26. | Revised-Draft-2025-2026-Transmission-Plan.pdf | CAISO 2022-2023 Transmission Plan
New Sigurd-Clover | New Line | 345 kV | 125 | 69 | PacifiCorp | Utah | Conceptual Planning | Preliminary planning. Expected in-service beyond PacifiCorp’s 10-year planning horizon; no current firm in-service date. | Local Transmission System Plan
New Spanish Fork- Mercer | New Line | 345 kV | 106 | 45 | PacifiCorp | Utah | Permitting | Routing study underway; construction expected to begin in 2027; expected in-service in 2028. | Project Website: Spanish Fork to Mercer Transmission Project
New Three Peaks- Purgatory Flat | New Line | 345 kV | 205 | 55 | PacifiCorp | Utah | Advanced Planning | Completed routing study in May 2026; permitting expected to being in 2026; construction expected to begin in 2031; expected in-service in 2033. | Project Website: Three Peaks to Purgatory Flat | Three Peaks to Purgatory Flat Transmission Line Project
New Townsend- Ashe | New Line | 500 kV | 2618 | 500 | None Identified | Washington, Montana, Idaho | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New Townsend- Midpoint 500kV Line | New Line | 500 kV | 2112 | 429 | Northwestern Energy/Grid United | Idaho, Montana | Newly Proposed | Northwestern and Grid United have entered into a letter of intent to explore transmission development. No project details have been determined. | WestTEC_10-year_Full_Report.pdf | northwesternenergy.com/docs/default-source/default-document-library/about-us/erp-irp/2026-mt-irp-public.pdf
New Walker- Bonanza 500kV Line | New Line | 500 kV | 2034 | 375 | None Identified | Oregon, Nevada | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
New Western Spirit- Hidden Mountain | New Line | 345 kV | 480 | 104 | PNM | New Mexico | Conceptual Planning | Listed as a "conceptual project" in PNMs 20-year transmission outlook | pnm_20-year-transmission-outlook
New Western Spirit-Chavez County | New Line | 345 kV | 525 | 136 | PNM | New Mexico | Conceptual Planning | Listed as a "conceptual project" in PNMs 20-year transmission outlook | pnm_20-year-transmission-outlook
North of Marion: Rebuild Marion- Chemawa- Pearl 500kV Line | Rebuild | 500 kV | 225 | 47 | BPA | Oregon | Advanced Planning | Combining Marion upgrades 1 and 2. Scoping to start in late 2026. | August 19 GAT Update Workshop | EGP-20-Public-Workshop-17-Oct-2024.pdf
North of Pearl 500kV Upgrade (incl. Pearl- Keeler #2 500kV) | New Line | 500 kV | 88 | 19 | BPA | Oregon | Advanced Planning | Scoping starts in early 2026; estimated in-service in 2033. | August 19 GAT Update Workshop | GERP-Project-Update.pdf
Path 36 TOT 3 Upgrade | Reconductor | 345 kV, 230kV, 115kV | 36 | 75 | None Identified | Colorado, Wyoming | Newly Proposed | Project was also identified by the Colorado Electric Transmsision Authority 2024 study. | WestTEC_10-year_Full_Report.pdf | CETA+Transmission+Study+Final+Report+-+241012.pdf
Pinnacle Peak- Rogers 230kV Restoration Project | Rebuild | 230 kV | 14 | 3 | WAPA | Arizona | In Service | In-service in February 2024. | WAPA Project Update
Raver- Paul: Chehalis- Cowlitz Tap 230kV (Chehalis-Covington 230 kV Line Upgrade) | Reconductor | 230 kV | 95 | 35 | BPA | Washington | Advanced Planning | Expected in-service in 2028 | EGP-10-Project-Summaries.pdf | August 19 GAT Update Workshop
Ready WY: Sweetgrass- Bluffs 230kV Line, West Cheyenne- Sweetgrass 230kV Line, West Cheyenne- Windstar 230kV Line | New Line | 230 kV | 260 | 260 | Black Hills Energy | Wyoming | In Service | In-service in late 2025 | Project Website: Ready Wyoming: powering the future ¦ Black Hills Energy
Rebuild Big Eddy- Ostrander- Pearl 500kV Line (Big Eddy – Chemawa 230/500 kV Line Upgrade) | Rebuild | 500 kV | 670 | 91 | BPA | Oregon | Advanced Planning | Project is planned to complete scoping in the fall of 2025; estimated in-service in 2033. | August 19 GAT Update Workshop | EGP-10-Project-Summaries.pdf
Rebuild Clines Corner- Guadelupe- Taiban Mesa | Rebuild | 345 kV | 940 | 110 | None Identified | New Mexico | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Rebuild DMP-Vail (part of Vail-Tortolita Project) | Rebuild | 230 kV | 24 | 12 | Tuscon Electric Power | Arizona | Advanced Planning | Construction began in September 2024; Expected In-Service in Q4 2027 | Project Website: Vail to Tortolita 230 Kilovolt Transmission Line – Tucson Electric Power | TEP 2026 APR.pdf
Rebuild Tortolita- DMP (part of Vail-Tortolita Project) | Rebuild | 230 kV | 104 | 52 | Tuscon Electric Power | Arizona | Advanced Planning | Construction began in September 2024; Expected In-Service in Q4 2027 | Project Website: Vail to Tortolita 230 Kilovolt Transmission Line – Tucson Electric Power | TEP 2026 APR.pdf
Rebuild Grand Coulee- Columbia- Schultz | Rebuild | 500 kV | 1079 | 98 | BPA | Washington | Advanced Planning | Scoping starts in early 2026; estimated in-service in 2035. | EGP-20-Project-Summaries Update | August 19 GAT Update Workshop
Rebuild Pearl- Chemawa 230kV Line (part of North of Marion #1 project) | Rebuild | 230 kV | 50 | 25 | BPA | Oregon | Advanced Planning | Scoping starts in late 2026. | EGP-20-Project-Summaries Update | August 19 GAT Update Workshop
Rebuild Schultz- Olympia | Rebuild | 500 kV | 508 | 131 | BPA | Washington | Advanced Planning | Scoping starts in late 2026, estimated ISD is 2035. | EGP-20-Project-Summaries Update | August 19 GAT Update Workshop
Reconductor Amrad-Chavez | Reconductor | 345 kV | 49 | 65 | None Identified | New Mexico | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Reconductor Colorado River-Red Bluff 500kV #1 Line | Reconductor | 500 kV | 50 | 32 | CAISO - Souther California Edison | California | Advanced Planning | CAISO selected project in 2022-23 plan; currently in preliminary engineering and pending CPUC permit; expected in-service in December 2028. | CAISO 2022-2023 Transmission Plan | presentation-southern-california-edison-transmission-development-forum-jul-29-2026.pdf
Reconductor Diamond Tail- B-A Circuit 1 & 2 Line | Reconductor | 345 kV | 15 | 10 | None Identified | New Mexico | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Reconductor Keeler- Pearl 500kV #1 Line (North of Pearl 500kV upgrade) | Reconductor | 500 kV | 40 | 18 | BPA | Oregon | Advanced planning | Scoping starts in early 2026; estimated in-service in 2033. | EGP-20-Public-Workshop-17-Oct-2024.pdf | August 19 GAT Update Workshop
Reconductor Laramie River- Dave Johnston 230kV Line | Reconductor | 230 kV | 37 | 77 | None Identified | Wyoming | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Reconductor Mead-Perkins | Reconductor | 500 kV | 252 | 242 | None Identified | Arizona, Nevada | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Reconductor Ostrander- Pearl #1 500 kV Line | Reconductor | 500 kV | 21 | 20 | BPA | Oregon | Advanced Planning | Scoping starts in late 2026; estimated in-service in 2033. | EGP-20-Project-Summaries-120324-update.pdf | August 19 GAT Update Workshop
Reconductor Otero- Picante | Reconductor | 345 kV | 11 | 15 | None Identified | New Mexico | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Reconductor Rio Puerco- Pintado Circuit 1 | Reconductor | 345 kV | 74 | 63 | PNM | New Mexico | Conceptual Planning | PNM includes Four Corners to Rio Puerco and Ambrosia to West Mesa and Ambrosia to Coronado in their utility report. These projects meet the same Albuquerque to Arizona transmission need that this project meets. | 20-Year Transmission Planning Outlook
Reconductor Sams Valley- Whitestone 230kV with ACCC Conductor | Reconductor | 230 kV | 2 | 2 | None Identified | Oregon | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
RioSol | New Line | 500 kV | 2400 | 550 | RioSol/NM RETA | New Mexico, Arizona | Permitting | Expected to begin construction in 2026; expected in-service in 2028. | Project Website: RioSol Transmission Project - RETA New Mexico
San Juan Phase Shifter #3 | New Phase-Shifter |  | 26 | N/A | None Identified | New Mexico | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Second Mead- Market Place 500kV Line | New Line | 500 kV | 79 | 14 | None Identified | Nevada | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Six Mile Canyon Substation | Substation |  | 250 | N/A | BPA | Oregon | Advanced Planning | In design phase; estimated in-service in 2029. | BPA 2026 WECC Progress Report | August 19 GAT Update Workshop
South of Allston: Rebuild Ross-Rivergate 230kV Line | Rebuild | 230 kV | 50 | 8 | BPA | Washington, Oregon | Advanced Planning | In design phase; estimated in-service in 2031. | August 19 GAT Update Workshop | EGP-10-Project-Summaries.pdf
South of Knight: Reconductor Rock Creek- John Day | Reconductor | 500 kV | 37 | 14 | BPA | Washington, Oregon | Advanced Planning | In design phase; estimated in-service in 2030. | August 19 GAT Update Workshop | evolving-grid-project-summaries.pdf
Southeast Power Link | New Line | 230 kV | 71 | 7 | Salt River Project | Arizona | In Service | In-service in December 2024. | Project Website: Southeast Power Link project ¦ SRP
Southern Nevada MVAR Support | New Shunt |  | 5 | N/A | None Identified | Nevada | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
SunZia | New Line | 525 kV | 1800 | 552 | Pattern Energy | New Mexico, Arizona | In Service | In-service in June 2026. | Press Release: The US's largest clean energy project is generating power | Pattern Energy - SunZia Comes Online, Transforming Power Delivery in the United States - Advanced Power Alliance
SWIP-North | New Line | 500 kV | 1230 | 285 | LS Power/Idaho Power/ CAISO | Idaho, Nevada | Under Construction | Construction begun in mid-2026; estimated in-service in 2029. | Project Website: SWIP-North - Idaho Power | Work begins on $1bn Southwest Intertie Project – North in US
Ten West Link | New Line | 500 kV | 555 | 125 | CAISO - DCR Transmission, L.L.C. | Arizona, California | In Service | In-service in 2024. | Press Release: Ten West Link Transmission Line Becomes Operational, Expanding the Grid Between California and the Desert Southwest
TransWest Express | New Line | 500 kV | 3000 | 732 | Anschutz Corporation | Utah, Colorado, Wyoming, Nevada | Under Construction | BLM permits completed in 2023; construction began in 2023; estimated in-service in 2031-32 | Project Website: TransWest Express Transmission Project, USA | TransWest Express LLC
Uprate Hemingway- Summer Lake Circuit 1 via Substation Upgrades | Uprate | 500 kV | 55 | NA | None Identified | Idaho, Oregon | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf
Western Colorado MVAR Support | New Shunt |  | 21 | N/A | None Identified | Colorado | Newly Proposed |  | WestTEC_10-year_Full_Report.pdf

## Project Stages (hidden)
Project Name | Line Type | Project Status v1 | Cost ($M) | Miles | State | Notes | Source
SunZia | New Line | Complete | 1800 | 552 | New Mexico, Arizona |  | https://electrek.co/2026/04/17/the-us-largest-clean-energy-project-just-installed-242-giant-wind-turbines/
New Afton North-Airport | New Line | Early Permitting | 2 | 12 | New Mexico | stakeholder meeting about land use and routing took place in march | Notice of NMSLO Public Meeting for Afton North to Airport Transmission Line Project -Las Cruces ¦ NM State Land Office
New Afton-Afton North | New Line | Early Permitting | 2 | 1 | New Mexico | may not require a CPCN because its very short
Bolo Tie | New Line | Late Permitting | 168 | 35 | New Mexico | Open solicitaiton process ends in August | Bolo Transmission Open Solicitation
New Western Spirit-Chavez County | New Line | Planned | 525 | 136 | New Mexico | Listed as a "conceptual project" in PNMs 20-year transmission outlook | pnm_20-year-transmission-outlook_92025
New Western Spirit- Hidden Mountain | New Line | Planned | 480 | 104 | New Mexico | Listed as a "conceptual project" in PNMs 20-year transmission outlook | pnm_20-year-transmission-outlook_92025
New Rio Puerco- Prosperity | New Line | Late Permitting | 195 | 36 | New Mexico | Filed a CPCN but unclear whether it has been granted yet or not | Application and Notice.pdf
RioSol | New Line | Late Permitting | 2400 | 550 | New Mexico, Arizona | ROW application - interstate project may not require a CPCN | RioSol Transmission Project - RETA New Mexico
Reconductor Amrad-Chavez | Reconductor | Unplanned | 49 | 65 | New Mexico |  | WestTEC_10-year_Full_Report.pdf
Reconductor Otero- Picante | Reconductor | Unplanned | 11 | 15 | New Mexico |  | WestTEC_10-year_Full_Report.pdf
New Rio Puerco- San Juan Circuit 2 | New Line | Planned | 163 | 41 | New Mexico | PNM is studying this need as a high priority in their 10 year and 20 year transmission plans as well as their IRP
Rebuild Clines Corner- Guadelupe- Taiban Mesa | Rebuild | Unplanned | 940 | 110 | New Mexico |  | WestTEC_10-year_Full_Report.pdf
New Four Corners- San Juan Circuit 2 | New Line | Planned | 49 | 10 | New Mexico | PNM is studying this need as a high priority in their 10 year and 20 year transmission plans as well as their IRP
New Four Corners- Pintado Circuit 2 | New Line | Planned | 312 | 81 | New Mexico | PNM is studying this need as a high priority in their 10 year and 20 year transmission plans as well as their IRP
Reconductor Diamond Tail- B-A Circuit 1 & 2 Line | Reconductor | Unplanned | 15 | 10 | New Mexico |  | WestTEC_10-year_Full_Report.pdf
Reconductor Rio Puerco- Pintado Circuit 1 | Reconductor | Planned | 74 | 63 | New Mexico | PNM is studying this need as a high priority in their 10 year and 20 year transmission plans as well as their IRP
Arroyo Phase Shifter #2 | New Transformer | Unplanned | 31 | N/A | New Mexico |  | WestTEC_10-year_Full_Report.pdf
San Juan Phase Shifter #3 | New Transformer | Unplanned | 26 | N/A | New Mexico |  | WestTEC_10-year_Full_Report.pdf
New Jojoba to Rudd 500kV Line | New Line | Early Permitting | 146 | 31 | Arizona | Held open houses in Oct to help identify potential routes, beginning to work with BLM to complete environmental review | Cotton Transmission Corridor 500kV/230kV ¦ APS
New Hassayampa Pinal West #2 Line | New Line | Late Permitting | 244 | 51 | Arizona |  | Palo Verde to Pinal West 500 kV transmission project ¦ SRP
Southeast Power Link | New Line | Complete | 71 | 7 | Arizona |  | Southeast Power Link project ¦ SRP
Rebuild DMP-Vail | Rebuild | Under Construction | 24 | 12 | Arizona |  | Vail to Tortolita 230 Kilovolt Transmission Line – Tucson Electric Power
Rebuild Tortolita- DMP | Rebuild | Under Construction | 104 | 52 | Arizona |  | Vail to Tortolita 230 Kilovolt Transmission Line – Tucson Electric Power
New Golden Valley | New Line | Late Permitting | 64 | 17 | Arizona | no record that construction has begun | Golden Valley 230 kV – UniSource Energy Services
Ten West Link | New Line | Complete | 555 | 125 | Arizona, California |  | Ten West Link Transmission Line Becomes Operational, Expanding the Grid Between California and the Desert Southwest
New 345/230kV Transformer at Copper Verde | New Transformer | Unplanned | 10 | N/A | Arizona |  | WestTEC_10-year_Full_Report.pdf
New 500/345kV Transformer at Coronado | New Transformer | Unplanned | 20 | N/A | Arizona |  | WestTEC_10-year_Full_Report.pdf
Reconductor Mead-Perkins | Reconductor | Unplanned | 252 | 242 | Arizona, Nevada |  | WestTEC_10-year_Full_Report.pdf
New Mead- Liberty- West Wing | New Line | Unplanned | 1400 | 273 | Arizona |  | WestTEC_10-year_Full_Report.pdf
New 345/230kV Transformers at Liberty and Peacock | New Transformers | Unplanned | 29 | N/A | Arizona |  | WestTEC_10-year_Full_Report.pdf
Pinnacle Peak- Rogers 230kV Restoration Project | Rebuild | Complete | 14 | 3 | Arizona |  | WAPA BLANK PowerPoint Presentation
New Pinal Central-ED5 230kV Line | New Line | Under Construction | 44 | 19 | Arizona |  | Western Area Power Administration
New North Gila- Imperial Valley #2 500kV line | New Line | Early Permitting | 340 | 85 | Arizona | Permitting expected to begin in third quarter of 2025 | New Power Line Aims to Boost Grid Reliability in Imperial Valley - Calexico Chronicle
Bouse Upgrade | New Line | Late Permitting | 47 | 20 | Arizona, California | WAPA released final EA in 2022 and a FONSI in 2023 | Bouse Upgrade Project, DOE/EA-2106 – Western Area Power Administration
TransWest Express | New Line | Under Construction | 3000 | 732 | Utah, Colorado, Wyoming, Nevada |  | TransWest Express Transmission Project, USA
Energize the existing Red Butte- St. George Line at 345kV | New Line |  | 75 | 20 | Utah | unclear…
New Oquirrh-Terminal #3 and #4 Double Circuit Line | New Line | Under Construction | 52 | 14 | Utah |  | Generation Interconnection
New Sigurd-Clover | New Line | Planned | 125 | 69 | Utah
New Spanish Fork- Mercer | New Line | Late Permitting | 106 | 45 | Utah
New Three Peaks- Purgatory Flat | New Line | Planned | 205 | 55 | Utah
Energy Gateway | New Line | Under Construction | 8200 | 2300 | Utah, Idaho, Colorado, Wyoming | Built in segments: some are complete, some are in permitting stages, and some are under construction
Colorado's Power Pathway | New Line | Under Construction | 1700 | 550 | Colorado | Built in segments: some are complete, some are in permitting stages, and some are under construction
Western Colorado MVAR Support | New Shunt | Unplanned | 21 | N/A | Colorado
New 345/230kV Transformer at Grand Junction | New Transformer | Unplanned | 10 | N/A | Colorado
Path 36 TOT 3 Upgrade | Reconductor | Unplanned | 36 | 75 | Colorado, Wyoming
New Badger Creek- Big Sandy 230kV Line | New Line | Planned | 86 | 80 | Colorado
Big Sandy- Burlington 230kV Uprate | Rebuild | Late Permitting | 8 | 81 | Colorado | Big Sandy Burlington did not require a CPCN- https://tristate.coop/tri-state-moving-forward-1865-million-transmission-system-upgrades?utm_source=chatgpt.com
New Boone-Huckleberry 230kV Line | New Line | Under Construction | 40 | 30 | Colorado
New Burlington- Lamar 230kV Line | New Line | Complete | 107 | 107 | Colorado
Ault-Husky 230kV Line Upgrade | Rebuild | Complete | 9 | 5 | Colorado
Montana to Washington | Uprate | Planned | 545 | 90 | Washington, Montana, Idaho
Cross Cascades North Upgrade TSEP 2022 | Reconductor | Planned | 400 | 77 | Washington
Cross Cascades Project | New Line | Planned | 3700 | 235 | Washington, Oregon
Rebuild Grand Coulee- Columbia- Schultz | Rebuild | Planned | 1100 | 98 | Washington
Rebuild Schultz- Olympia | Rebuild | Planned | 508 | 131 | Washington
South of Knight: Reconductor Rock Creek- John Day | Reconductor | Planned | 37 | 14 | Washington, Oregon
Raver- Paul: Chehalis- Cowlitz Tap 230kV | Reconductor | Planned | 95 | 35 | Washington
South of Allston: Rebuild Ross-Rivergate 230kV Line | Rebuild | Planned | 50 | 8 | Washington, Oregon
New Townsend- Ashe | New Line | Unplanned | 2600 | 500 | Washington, Montana, Idaho
SWIP-North | New Line | Late Permitting | 545 | 90 | Idaho, Nevada
Longhorn to Hemingway (B2H) (Boardman to Hemingway) | New Line | Under Construction | 1200 | 290 | Idaho, Oregon
New Hemingway to Bowmont #2 230kV Line | New Line | Planned | 29 | 13 | Idaho
New Hubbard to Bowmont 230kV Line | New Line | Under Construction | 36 | 16 | Idaho
New Mayfield 230kV Substation and Transmission Lines | New Line | Early Permitting | 32 | 8 | Idaho | Submitted a CUP in 2025
New Mayfield Substation to Boise Bench Substation 230kV Line | New Line | Planned | 50 | 20 | Idaho
New Mayfield Substation to Chip Substation 230kV Line | New Line | Planned | 41 | 16 | Idaho
New Mayfield Substation to South Boise Substation 230kV Line | New Line | Planned | 45 | 21 | Idaho
New Townsend- Midpoint 500kV Line | New Line | Unplanned | 2100 | 429 | Idaho, Montana
Uprate Hemingway- Summer Lake Circuit 1 via Substation Upgrades | Uprate | Unplanned | 55 | 242 | Idaho, Oregon
Bonanza to Lower Columbia 500kV Reinforcement Project- Longhorn to Bonanza Line | New Line | Planned | 1300 | 274 | Oregon
Rebuild Big Eddy- Ostrander- Pearl 500kV Line | Rebuild | Planned | 670 | 91 | Oregon
North of Marion: Rebuild Marion- Chemawa- Pearl 500kV Line | Rebuild | Planned | 225 | 47 | Oregon
North of Pearl 500kV Upgrade (incl. Pearl- Keeler #2 500kV) | New Line | Planned | 88 | 19 | Oregon
Reconductor Ostrander- Pearl #1 500 kV Line | Reconductor | Planned | 21 | 20 | Oregon
Bonanza to Lower Columbia 500kV Reinforcement Project- Six Mile Substation | Substation | Planned | 250 | N/A | Oregon
Bonanza to Lower Columbia 500kV Reinforcement Project- Bonanza Substation | Substation | Planned | 300 | N/A | Oregon
New Bethel- Round Butte 500kV Line | New Line | Planned | 857 | 100 | Oregon
New Corral- Grassland Annex 500kV line | New Line | Planned | 659 | 159 | Oregon
New Corral- Snow Goose 500kV line | New Line | Planned | 763 | 161 | Oregon
New Grassland Annex- B2H Tap Substation 500kV Line | New Line | Planned | 76 | 16 | Oregon | Unclear…
Reconductor Keeler- Pearl 500kV #1 Line | Reconductor | Unplanned | 40 | 18 | Oregon
New Walker- Bonanza 500kV Line | New Line | Unplanned | 2000 | 375 | Oregon, Nevada
Six Mile Canyon Substation | Substation | Planned | 250 | N/A | Oregon
Bonanza Substation | Substation | Planned | 300 | N/A | Oregon
Rebuild Pearl- Chemawa 230kV Line | Rebuild | Planned | 50 | 25 | Oregon
New Bonanza- La Pine 230kV line | New Line | Planned | 150 | 53 | Oregon
New Harborton- Trojan #3 & #4 230kV Line | new Line | Planned | 135 | 33 | Oregon
Reconductor Sams Valley- Whitestone 230kV with ACCC Conductor | Reconductor | Unplanned | 2 | 2 | Oregon
New Keeler- Pearl 500kV #2 Line | New Line | Unplanned | 195 | 38 | Oregon
Colstrip- Broadview 500kV Series Capacitor Upgrade | Series Capacitor | Unplanned | 67 | N/A | Montana
Ready WY: Sweetgrass- Bluffs 230kV Line, West Cheyenne- Sweetgrass 230kV Line, West Cheyenne- Windstar 230kV Line | New Line | Complete | 260 | 260 | Wyoming
Reconductor Laramie River- Dave Johnston 230kV Line | Reconductor | Unplanned | 32 | 77 | Wyoming
New Lantern- Comstock Meadows 345kV Line | New Line | Planned | 124 | 33 | Nevada
Greenlink West | New Line | Under Construction | 2800 | 350 | Nevada
Greenlink North | New Line | Late Permitting | 1400 | 235 | Nevada
Second Mead- Market Place 500kV Line | New Line | Unplanned | 79 | 14 | Nevada
New 500/345kV Transformer at Walker River | New Transformer | Unplanned | 19 | N/A | Nevada
Southern Nevada MVAR Support | New Shunt | Unplanned | 5 | N/A | Nevada
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DEFINITIONS Project Status v2 Not planned Not listed in utility planning processes/listed as proposed projects in WestTEC report Planning identified in utility planning processes/active planning Permitting Currently filing for permits but not all have been granted yet Fully Permitted Planned and permits are all granted, construction has not yet started In Construction In construction Complete In Service Reply: unplanned, planning, early permitting, late permitting, fully permitted, in construction, in service Reply: partially submitted permits vs all permits are submitted Reply: unplanned, planned, early permitting (partially submitted permits), late permitting (most/all permits are submitted), under construction, in service

## Status Definitions v1 (hidden)
Term | Definition | Column1
Unplanned | Identified in WestTEC study but not included in a utility, regional, or developer plan
Planned | Identified in utility resource or transmission plans, route alternatives being evaluated, permitting not yet initiated
Early Permitting | Route still being refined, environmental studies underway, major permit applications partially submitted | Is being granted a waiver of significant impact enough to be considered early permitting?
Late Permitting | Major permit applications submitted or approved, environmental review substantially complete or completed, awaiting final approvals, financing, procurement, or construction start | Is open soliciation process early or late permitting?
Under Construction | Physical construction activities have begun
In Service | Project has entered commercial operation

## Sheet2 (hidden)
Project Name | Upgrade Type | Project Status | Cost | Mileage | State | Sources | Column1 | Column2
Six mile canyon substation | Substation | Planning | $250 million | NA | Oregon | EGP-10-Project-Summaries.pdf
Bonanza substation | Substation | Planning | $300 million | NA | Oregon | subst
Rebuild Pearl- Chemawa 230 kV Line | Rebuild | Planning | $50 million | 25 | Oregon | EGP-20-Project-Summaries-120324-update.pdf
New bonanza- lapine 230kV line | New Line | Planning | $150 million | 53 | Oregon | EGP-10-Project-Summaries.pdf
Raver- paul: chehalis- cowlitz tap 230kV | Reconductor | Planning | $95 million | 35 | Washington | EGP-10-Project-Summaries.pdf
South of Allston: Rebuild Ross- Rivergate 230kV Line | Upgrade | Planning | $50 million | 8 | Washington, Oregon | EGP-10-Project-Summaries.pdf
Reconductor Colorado River- Red Bluff 500kV #1 Line | Reconductor | Planning | $50 million | 32 | California | Edison Int'l Template
Humboldt to Fern Road 500kV Line | New Line | Planning | $1.4 billion | 140 | California | 2023-2024 Transmission Planning Process Approved Project Sponsor for the New Humboldt 500 kV Substation, with a 500/115 kV transformer, and 500 kV line to Collinsville [HVDC operated as AC] and New Humboldt to Fern Road 500KV Line Projects ¦ California ISO
Humboldt to Collinsville 500kV line | New Line | Planning | $2.7 billion | 260 | California | 2023-2024 Transmission Planning Process Approved Project Sponsor for the New Humboldt 500 kV Substation, with a 500/115 kV transformer, and 500 kV line to Collinsville [HVDC operated as AC] and New Humboldt to Fern Road 500KV Line Projects ¦ California ISO
New San jose Area HVDC 230kV Line | New Line | Planning | $726 million | 12 | California | Bay Area 230 kV Underground Line Project Advances Grid Reliability in Northern California
New Imperial Valley- north of SONGS 500kV Line and substation | New Line | Planning | $2.3 billion | 145 | California | Update to Imperial Valley: North of SONGS 500 kV Transmission Line and North of SONGS Substation Approved Project Sponsor ¦ California ISO
New serrano- del amo- mesa 500kV Line |  |  |  |  | California
New North of SONGS- Serrano 500kV Line |  |  |  |  | California
Ready WY: Sweetgrass- Bluffs 230kV Line, West Cheyenne- Sweetgrass 230kV Line, west Cheyenne windstar 230kV Line | New Line | Complete | $260 million | 260 | Wyoming | Microsoft PowerPoint - Ready Wyoming - NE Briefing_edit rh.v3.pptx - Read-Only | Black Hills Corp. Completes Ready Wyoming 260-Mile Electric Transmission Expansion Project ¦ MarketScreener
Greenlink North | New Line | In construction | $1.4 billion | 235 | Nevada | Greenlink Nevada ¦ NV Energy
Greenlink West | New Line | In construction | $2.8 billion | 350 | Nevada | Greenlink Nevada ¦ NV Energy
New Lantern- Comstock Meadows 345 kV line | New Line | Planning | $124 million | 33 | Nevada | NEV 2024 APR.pdf
New Harborton- Trojon #3 & #4 230kV line | New Line |  | $135 million | 33 | Oregon |  |  | hard to find info on #3 and #4
New badger creek- big sandy 230kV line | New Line | Planning | $86 million | 80 | Colorado | TSGT 2025 APR.pdf |  | Tri-State moving forward with $186.5 million in transmission system upgrades ¦ Tri-State Generation and Transmission Association, Inc
Big sandy- burlington 230kV uprate | Rebuild |  | $8 million | 81 | Colorado | TSGT 2025 APR.pdf |  | Tri-State moving forward with $186.5 million in transmission system upgrades ¦ Tri-State Generation and Transmission Association, Inc
New boone- huckleberry 230kv Line | New Line |  | $40 million | 30 | Colorado | Appendix E - Tri-State Project Sheets.pdf
New burlington- lamar 230kv Line | New Line |  | $107 million | 107 | Colorado | Tri-State Energizes Colorado Transmission Line
Bouse upgrade | New line |  | $47 million | 20 | Arizona | Bouse Upgrade Project, DOE/EA-2106 – Western Area Power Administration
Ault-Husky 230kV line upgrade | Rebuild |  | $9 million | 5 | Colorado