## Instructions
Electrify Program Outreach Timeline Playbook
Purpose: | The goal of this Outreach Timeline Playbook is to help local governments and community organizations develop their outreach timeline. While this playbook should be developed in advance of the program’s launch, it should also be a living document that is updated throughout the program during all check-in meetings to continue to stay organized.
Instructions | You may use or modify this template in whatever way is most helpful. The RMI team does not expect credit or citation for any of this material. Follow the instructions and comments as guidance.
Sources: | This template was created using the best practices our team identified in NYSERDA’s Community Outreach Planning Form and our internal expertise.
Disclaimer: | RMI makes no warranties or guaranties about the completeness or accuracy of this information. Any material in this template should be used at your own risk and in your sole discretion and by its use you are acknowledging that the RMI team shall not be liable for any damages in connection with the use of this template. We do not expect credit or citation for any of this material.

## Outreach Plan
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | OUTREACH STRATEGY | [7 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37
| Instructions | 1. Input today's date in cell D3 and the campaign's launch date in cell F3 to autopopulate the Gantt chart dates. 2. Under each outreach method, input the purpose, responsible organization and team member, notes, and start/end dates. | [6 empty] | 2025-01-01 | [6 empty] | 2025-01-08 | [6 empty] | 2025-01-15 | [6 empty] | 2025-01-22 | [6 empty] | 2025-01-29 | [6 empty] | 2025-02-05 | [6 empty] | 2025-02-12 | [6 empty] | 2025-02-19 | [6 empty] | 2025-02-26 | [6 empty] | 2025-03-05 | [6 empty] | 2025-03-12 | [6 empty] | 2025-03-19 | [6 empty] | 2025-03-26 | [6 empty] | 2025-04-02 | [6 empty] | 2025-04-09 | [6 empty] | 2025-04-16 | [6 empty] | 2025-04-23 | [6 empty] | 2025-04-30 | [6 empty] | 2025-05-07 | [6 empty] | 2025-05-14 | [6 empty] | 2025-05-21 | [6 empty] | 2025-05-28 | [6 empty] | 2025-06-04 | [6 empty] | 2025-06-11 | [6 empty] | 2025-06-18 | [6 empty] | 2025-06-25 | [6 empty] | 2025-07-02 | [6 empty] | 2025-07-09 | [6 empty] | 2025-07-16 | [6 empty] | 2025-07-23 | [6 empty] | 2025-07-30 | [6 empty] | 2025-08-06 | [6 empty] | 2025-08-13 | [6 empty] | 2025-08-20 | [6 empty] | 2025-08-27 | [6 empty] | 2025-09-03 | [6 empty] | 2025-09-10
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. |  | Planning Start Date: | 2025-01-01 | Program Launch Date: | 2025-06-01 | time axis 2025-01-01 to 2025-09-16
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | Outreach Method | Outreach Purpose | Responsible Organization/Outlet | Responsible Team Member | Notes/Result | START | END | DAYS | time axis 2025-01-01 to 2025-09-16
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Emails
|  | [Draft program launch email templates] |  |  |  | 2025-01-01 | 5/30/202
Local Media
|  | [Draft media advisories] |  |  |  | 2025-01-01 | 5/30/202
Sample phase title block | Social Media
|  | [Draft social media templates] |  |  |  | 2025-01-01 | 5/30/202 | -665688
Sample phase title block | Canvassing/Community Events
|  | [Finalize launch event location, date, and speakers] |  |  |  | 2025-01-01 | 5/30/202 | -665688
Heat Pump Ambassadors
|  | [Identify and recruit heat pump ambassadors] |  |  |  | 2025-01-01 | 5/30/202
Sample phase title block | Heat Pump Tours
|  | [Identify and recruit those offering to provide a heat pump tour] |  |  |  | 2025-01-01 | 5/30/202 | -665688
Insert new rows ABOVE this one
Formulas:
Week 2 = [Week 2, row below]
Week 3 = [Week 3, row below]
Week 4 = [Week 4, row below]
Week 5 = [Week 5, row below]
Week 6 = [Week 6, row below]
Week 7 = [Week 7, row below]
Week 8 = [Week 8, row below]
Week 9 = [Week 9, row below]
Week 10 = [Week 10, row below]
Week 11 = [Week 11, row below]
Week 12 = [Week 12, row below]
Week 13 = [Week 13, row below]
Week 14 = [Week 14, row below]
Week 15 = [Week 15, row below]
Week 16 = [Week 16, row below]
Week 17 = [Week 17, row below]
Week 18 = [Week 18, row below]
Week 19 = [Week 19, row below]
Week 20 = [Week 20, row below]
Week 21 = [Week 21, row below]
Week 22 = [Week 22, row below]
Week 23 = [Week 23, row below]
Week 24 = [Week 24, row below]
Week 25 = [Week 25, row below]
Week 26 = [Week 26, row below]
Week 27 = [Week 27, row below]
Week 28 = [Week 28, row below]
Week 29 = [Week 29, row below]
Week 30 = [Week 30, row below]
Week 31 = [Week 31, row below]
Week 32 = [Week 32, row below]
Week 33 = [Week 33, row below]
Week 34 = [Week 34, row below]
Week 35 = [Week 35, row below]
Week 36 = [Week 36, row below]
Week 37 = [Week 37, row below]